## Project Charter
Project Charter
General Project Information
Project Title | Xpro AI-Cancer Prediction Project
Project Manager | Dinesh Kumar Sariga
Project Owner | Saibal
Mentor | Sneha G
Project Start Date | 2025-08-06
Project End Date | 2025-09-20
Purpose of the Project
The purpose of this project is to design and implement an AI/ML-based system for predicting cancer presence using synthetic clinical data. It aims to provide hands-on experience in the complete AI project lifecycle, starting from data generation and cleaning to model development, evaluation, and deployment in a simulated environment.
Project Scope
Project Scope |  | Complete
Generation of synthetic cancer-related datasets (≥1000 patient records with demographics, biomarkers, and clinical factors).
Injection of anomalies (nulls, duplicates) and creation of a robust data cleaning pipeline.
Validation of cleaned datasets to ensure readiness for machine learning model development.
Drafting of System Requirement Specification (SRS) and Project Management Planning (PM Plan) documents.
Future sprints will cover model training, evaluation, explainability, and preparation for deployment in a simulated environment.
Project Team
Role | Name |  | Est Benefit
Data Scientist | HamsaPriya M
ML Engineer | Harshitha P M
Software Engineer | Deepa D J
MLOps Engineer | Hrudhay H
Business Analyst | Rakshitha G
Risk Manager | Sampreeth C H
Deliverables
S1W1 | Data Preparation Script
S1W1 | Synthetic & Cleaned Data File
S1W2 | System Requirement Specification
S1W2 | PM Planning Document
S2W3 | Python Scripts for Feature Engineering & Model Training
S2W3 | Processed Dataset
S1W3 | Model Metrics
S2W4 | Prediction Report
S2W4 | Updated PM Documentation
S3W5 | Optimized Model Code
S3W5 | Final PredictionDataset
S3W6 | Final Evaluation Report
S3W6 | Final Project Presentation
Milestone Schedule
Role | Start Date Target Completion Date |  | Est Benefit
Data Preparation | 06-08-2025 18-08-2025
ML Model Development
Model Optimization
Integration & Deployment
Risks and Issues
Clinical Risks | Misclassification or false predictions could delay or misguide treatment
Regulatory Risks | Gaps in CDSCO/FDA compliance may delay approvals.
Data Privacy Concernbs | Risks of patient data leakage under DPDP Act 2023 / HIPAA.
Operational Risks | Lack of proper MLOps tracking and reproducibility issues.
Adoption Challenges | Doctors may distrust black-box AI predictions without explainability.
Security Threats | Potential cyberattacks on hospital systems or AI APIs.
Litigation Risks | Exposure to malpractice claims, privacy violation suits, or IP ownership disputes.

## Project Plan
Project Plan
[9 empty] | Sprint 1 | [11 empty] | Sprint 2 | [11 empty] | Sprint 3
[6 empty] | W1 | [5 empty] | W2 | [5 empty] | W3 | [5 empty] | W4 | [5 empty] | W5 | [5 empty] | W6
Sprint | Function | Sub-Function | Phase Name | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36
| Data Engineering | Data Collection & Preparation | Synthetic & Cleaned Data File​ | bar: D1 to W1 D4
Data Preparation Script | bar: W1 D3 to W1 D6
Sprint 01 | Project Management | Documentation | System Requirement Specification Document (SRS) | bar: W1 D7 to W2 D9
Project Plan Document | bar: W2 D10 to W2 D12
|  | Feature Engineering | Python Scripts for Feature Engineering | bar: W2 D13 to W2 D14
| Machine Learning |  | Processed Dataset | bar: W3 D15 to W3 D16
Sprint 02 |  | Model Training & Evaluation | Model Metrics | bar: W3 D17 to W3 D18
Prediction Report | bar: W3 D19 to W4 D21
| Project Management | Documentation | PM Documentation | bar: W4 D22 to W4 D24
|  | Model Optimization | Optimized Model Code | bar: W4 D25 to W5 D27
Sprint 03 |  |  | Final Prediction Dataset | bar: W5 D28 to W5 D30
| Deployement & Delivery | Finalization & Validation | Final Evaluation Report | bar: W5 D31 to W6 D33
|  | Presentation | Final Project Presentation | bar: W6 D34 to W6 D36
Sprint 1
Sprint 2
Sprint 3